## Problem_Statement
Netflix, Expansion into Online Education ¦ Competitive Risk Problem Statements
Risk # | Risk Type | SWOT Quadrant | Competitive Pressure | Why Monitor Now | Linked KRI
1 | Strategic / Competitive (Negative Risk) | Threat | Coursera and Udemy have announced a merger (expected Q3 2026), creating a combined platform with 240M+ learners, 12,000+ courses, and deep university partnerships, directly threatening Netflix's ability to compete before its education division even launches. | The merger is expected to close within months. If Netflix does not accelerate its differentiation strategy now, the combined entity will set industry standards for credentialing, AI personalization, and corporate partnerships that Netflix will struggle to match. | Netflix education subscriber growth rate (month-over-month)
2 | Compliance / Technology (Negative Risk) | Threat | Established platforms such as Coursera and LinkedIn Learning already hold ISO 27001 and SOC 2 certifications and actively use data privacy compliance as a B2B sales differentiator. Netflix currently lacks these certifications, creating a gap that could disqualify it from enterprise contracts. | Stricter enforcement of FERPA and GDPR is accelerating across markets. Competitors are winning enterprise deals by leading with compliance credentials. Without equivalent certifications, Netflix risks losing institutional and corporate clients before it can build a track record. | Percentage of educational platform systems compliant with GDPR, FERPA, ISO 27001, and SOC 2
3 | Strategic (Positive Risk) | Opportunity | The digital education market is valued at USD 30.36 billion in 2026 and projected to reach USD 98.58 billion by 2031 (CAGR 26.57%). Over 40% of platforms still struggle with inconsistent accreditation and quality control, leaving a gap for a high-quality content-rich platform to capture corporate upskilling demand. | Corporate training budgets are expanding and existing platforms have not fully addressed the demand for premium, flexible micro-credential programs. Netflix's content production expertise and global reach make this a time-sensitive opportunity, especially before the Coursera-Udemy merger closes and consolidates the competitive landscape further. | Number of active B2B corporate learning partnerships signed within first 12 months

## KRI_Framework
Netflix, Competitive Risk KRI Framework with Traffic Light Thresholds
Risk # | Risk Type | Leading Indicator (KRI) | Metric / Unit | Monitoring Frequency | Green (Optimized) | Amber (Warning) | Red (Critical)
1 | Strategic / Competitive (Negative Risk) | Netflix education subscriber growth rate | Month-over-month % growth | Monthly | Above 8% monthly growth, subscriber acquisition on track; competitive differentiation working. | 4% to 8% monthly growth, growth slowing; review content strategy and partnership pipeline. | Below 4% monthly growth, immediate review required; escalate to senior leadership.
2 | Compliance / Technology (Negative Risk) | Platform compliance coverage rate | % of systems compliant with GDPR, FERPA, ISO 27001, SOC 2 | Monthly | 100% compliance, all systems certified; no regulatory exposure. | 95% to 99% compliance, gaps identified; remediation plan must be activated within 30 days. | Below 95% compliance, critical regulatory exposure; escalate immediately to Board and Legal.
3 | Strategic (Positive Risk) | B2B corporate learning partnership count | Number of signed enterprise partnerships | Quarterly | 5 or more partnerships within 12 months, on track to capture corporate market. | 2 to 4 partnerships within 12 months, below target; accelerate outreach and pilot programs. | Fewer than 2 partnerships within 12 months, opportunity at risk; strategic review required.

## Risk_Register
Netflix, Competitive Risk Register ¦ ALY6130 Assignment 2
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence/Impact | Likelihood Score | Impact Score | Priority (H/M/L) | Mitigation | Risk Owner | Open/Closed
1 | 2026-05-30 | Losing competitive ground in the online education market (Negative Risk) | The Coursera-Udemy merger (expected Q3 2026) creating a dominant platform with 240M+ learners, established credentialing infrastructure, and significant AI personalization advantages that Netflix does not yet possess | Netflix being unable to differentiate its education offering, resulting in low subscriber acquisition and failure to achieve target ROI within 24 months of launch | Strategic / Financial, reduced market penetration, lower subscriber acquisition, and potential discontinuation of the education division | 7 | 8 | H | Accelerate university partnership development; invest in exclusive content not available on merged competitor platform; launch Netflix-branded micro-credential pilot before Q3 2026 | Strategy & Product Team | Open
2 | 2026-05-30 | Failing to meet data privacy and security standards required by enterprise and institutional clients (Negative Risk) | Netflix's entertainment-focused data infrastructure not being compliant with FERPA, GDPR, ISO 27001, and SOC 2, certifications that competing platforms already hold and use as a B2B sales differentiator | Lost enterprise contracts, regulatory penalties under FERPA and GDPR, and reputational damage that prevents Netflix from entering the institutional education market | Compliance / Legal / Financial, regulatory fines, loss of B2B contracts, and reputational harm that undermines the entire education expansion | 7 | 8 | H | Initiate ISO 27001 and SOC 2 certification processes immediately; implement FERPA and GDPR compliance audits quarterly; assign dedicated data governance team for the educational platform | Cybersecurity & Data Governance Team | Open
3 | 2026-05-30 | Missing the opportunity to capture the rapidly growing corporate upskilling market (Positive Risk) | Slow execution in developing B2B learning solutions and Netflix-branded micro-credentials, combined with the window of opportunity narrowing as the Coursera-Udemy merger consolidates the competitive landscape | Failure to establish a foothold in the corporate training segment before competitors lock in enterprise clients, resulting in missed revenue in a market projected to reach USD 98.58 billion by 2031 | Strategic / Financial, missed revenue opportunity as corporate training budgets expand and competitors secure long-term enterprise contracts | 5 | 8 | M | Prioritize B2B outreach; develop micro-credential pilot with at least two accredited institutions within the first 12 months; establish dedicated corporate learning sales team | Strategy & Product Team | Open

## Risk_Calculation
Risk Calculation Sheet, Netflix Online Education Expansion
Probability of Occurrence | Score |  | Impact of Risk | Risk Heatmap
Very Unlikely | 1 |  | Very Low |  | Very Low (1) | Somewhat Low (2) | Moderate (4) | Somewhat High (6) | High (8) | Extremely High (9)
Somewhat Unlikely | 3 |  | Somewhat Low | Very Likely (9)
50-50 Possibility | 5 |  | Moderate | Somewhat Likely (7) |  |  |  |  | R1, R2
Somewhat Likely | 7 |  | Somewhat High | 50-50 (5) |  |  |  |  | R3
Very Likely | 9 |  | High | Somewhat Unlikely (3)
|  |  | Extremely High | Very Unlikely (1)
[5 empty] | Low Risk | Moderate Risk | High Risk
Risk Summary
Risk # | Risk Description | Likelihood Score | Impact Score
1 | Coursera-Udemy merger, competitive displacement risk (Negative Risk) | 7 | 8
2 | Data privacy compliance gap, enterprise market exclusion (Negative Risk) | 7 | 8
3 | Corporate upskilling market opportunity (Positive Risk) | 5 | 8

## References
References — Netflix Competitive Risk Register
# | Reference (APA Format) | Relevance to Assignment
1 | COSO. (2017). Enterprise risk management: Aligning risk with strategy and performance. Committee of Sponsoring Organizations of the Treadway Commission. | Framework used to develop KRIs and structure the risk identification process.
2 | Global Market Insights. (2024). E-learning market size & share report. GMI. https://www.gminsights.com/industry-analysis/elearning-market-size | Source for e-learning market size projection exceeding $600 billion by 2030, used in Risk 3 (positive risk).
3 | Mordor Intelligence. (2026). Digital education market size, growth report, forecast & share 2031. https://www.mordorintelligence.com/industry-reports/digital-education-market | Source for digital education market valuation (USD 30.36B in 2026, projected USD 98.58B by 2031, CAGR 26.57%), used in Problem Statement for Risk 3.
4 | Netflix, Inc. (2025). 2024 annual report. Netflix Investor Relations. https://ir.netflix.net/financials/annual-reports-and-proxies/default.aspx | Source for Netflix subscriber base (300M+) and financial performance data referenced in competitive analysis.
5 | Pantano, R. (n.d.). Introduction to risk management [Course presentation, Modules 1-2]. ALY6130, Northeastern University. | Course material used to structure risk statements, impact statements, KRIs, and traffic light thresholds.
6 | Project Management Institute. (2009). Practice standard for project risk management. PMI. | Referenced for risk management methodology and terminology used throughout the assignment.