NETFLIX EDTECH ENTRY (2026–2028)

Enterprise Risk Management Assessment

Group 4 members:

Adewole F. Adelana

Juliana Gyamfua

Thaise Gusson S. Domingos

Master of Professional Studies in Analytics

Northeastern University, College of Professional Studies

ALY6130 – Risk Management for Analytics

Professor: Abeba N. Turi

June 24, 2026

Background

Netflix, Inc. is one of the most recognized streaming platforms in the world, with over 300 million paid subscribers across more than 190 countries and approximately $39 billion in revenue in 2024 (Netflix, Inc., 2025). But subscriber growth in mature markets has slowed, and the streaming space is crowded enough that Netflix is actively looking at new directions. Online education is one of them. The global digital education market is projected to reach $98.58 billion by 2031, growing at 26.57% annually (Mordor Intelligence, 2026), and Netflix has real advantages to bring to it: an existing subscriber base, a proven recommendation algorithm, content production experience, and global brand recognition that most EdTech startups would take years to build.

The challenge is that EdTech is not just a content business. It requires academic credentials, data privacy compliance under frameworks like FERPA and GDPR, and the kind of institutional trust that platforms like Coursera and LinkedIn Learning have spent years building. That challenge got harder in May 2026 when Coursera completed its acquisition of Udemy, creating a combined platform with 290 million learners and 18,000 enterprise clients at a $2.5 billion valuation (Coursera, 2026). Netflix would be entering a market that just got a lot more consolidated.

This report was put together to give Netflix's leadership a clear picture of what that entry involves from a risk standpoint. It covers the three highest-priority risks identified through this analysis, how they were assessed qualitatively and quantitatively, and what the recommended response strategies are. The analysis was built in stages, starting with a SWOT framework and competitive landscape review, moving through a formal risk register and qualitative scoring process, and finishing with Monte Carlo simulation and machine learning modeling to quantify potential financial exposure.

Identification of risks

To identify the risks associated with this expansion, our team worked through a structured brainstorming process covering five dimensions: people, processes, technology, facilities, and external market conditions. Industry sources including HolonIQ, Gartner, and Stanford HAI were used alongside Netflix's own financial disclosures to ground the analysis in real data. The process surfaced ten core negative risks across four main areas: financial and ROI exposure, competitive and credibility threats such as academic brand acceptance and competitor market consolidation, technology and operational risks including AI governance, platform scalability, and vendor dependency, and regulatory risks around data privacy, accreditation, and content compliance.

That inventory was compiled into a Risk Register and scored using a 9x9 probability-impact matrix. After examining how the risks related to each other, three were selected for full assessment. All three scored 81, placing them in the Critical tier. What stood out was that they are not independent problems. The capital investment risk and the AI training data gap both point to the same underlying issue: Netflix is entering a market that requires infrastructure, credibility, and data assets it does not yet have. The competitive displacement risk from the Coursera-Udemy merger sits on top of both, because every month Netflix takes to close those gaps gives the merged platform more time to consolidate enterprise clients and academic partnerships that Netflix will need to compete for.

| ID | Risk Name | Category | Root Cause |
| --- | --- | --- | --- |
| R6 | Capital Investment Exceeding Projections | Financial | Technology diversification builds are consistently underestimated; Netflix gaming entry exceeded $1B with limited ROI |
| R16 | Coursera-Udemy Competitive Displacement | Competitive | Merger completed May 2026 creating a 290M-learner entity with enterprise relationships Netflix does not yet have |
| R28 | Limited Educational AI Training Data | Technical | Netflix lacks the educational interaction data needed to train competitive AI models; building this from scratch takes 3–5 years |

Table 1. Three critical risks selected for full assessment

Qualitative risk assessment

For the qualitative assessment, two methods were used: Scenario Analytics and Industry Fusion Analytics.

Scenario Analytics meant building three plausible scenarios for each risk. For R16, the base case has the merged Coursera-Udemy platform capturing 35–40% of the corporate upskilling market within 18 months; the downside case is Netflix losing ground before the education division becomes profitable; the optimistic case is Netflix differentiating through AI personalization and exclusive content before the competitor cements its position. For R6, scenarios ranged from a controlled $125M build to a $250M overrun driven by scope expansion. For R28, the scenarios mapped the gap between Netflix's entertainment recommendation data and what educational AI personalization requires.

Industry Fusion Analytics drew on HolonIQ's 2024 EdTech market report, Gartner's platform cost analysis, and Stanford HAI's 2024 AI Index to ground the probability and impact estimates in real market data.

Each risk scored 81 on the 9x9 matrix, placing all three in the Critical tier. The most important takeaway from this stage was not the scores but the timing: the competitive window in EdTech is closing faster than the capital and technology problems can be fixed, so the response to R16 needs to start before the platform is even ready.

| ID | Risk | Probability | Severity | Score | Rating |
| --- | --- | --- | --- | --- | --- |
| R6 | Capital Investment Overrun | 9 | 9 | 81 | Critical |
| R16 | Competitive Displacement | 9 | 9 | 81 | Critical |
| R28 | AI Training Data Gap | 9 | 9 | 81 | Critical |

Table 2. Qualitative risk scores (9x9 matrix)

Quantitative risk assessment

For the quantitative stage, three techniques were applied: the Indicators and Warning (I&W) method, Monte Carlo simulation with 10,000 iterations in Python/NumPy, and machine learning prediction using Random Forest. The I&W method works by assigning measurable leading indicators with Green/Amber/Red thresholds to each risk, so the team has specific signals to watch rather than waiting for something to go wrong. Monte Carlo simulation was used to model a range of financial outcomes under uncertainty rather than relying on a single estimate (Khadem et al., 2018).

For the ML component, a Random Forest model was used to predict the likelihood of each risk materializing. The inputs were the same indicators already being tracked in the KRI framework, including monthly subscriber growth rate, capital expenditure variance, dataset completeness, and partnership pipeline count. Since real historical data for Netflix's EdTech entry does not exist, synthetic data was generated based on benchmarks from HolonIQ and Class Central to simulate realistic market scenarios. The model outputs were then compared against the Monte Carlo results as a cross-check on the probability estimates for each risk.

R6: Initial capital investment exceeding projections

A 3-point estimate was applied with a low estimate of $50M, a base estimate of $125M, and a high estimate of $250M. The range reflects EdTech platform build benchmarks from Gartner (2024), which place enterprise-grade LMS development between $50M and $150M, and Netflix's own pattern of underestimating technology diversification costs, most clearly in its gaming initiative which exceeded $1 billion with limited subscriber impact (Netflix, Inc., 2025). The simulation returned a mean expected loss of $112.5M and a 90th percentile outcome of $168M. Probability of occurrence was estimated at 87%.

R16: Coursera-Udemy competitive displacement

A 3-point estimate was applied with a low estimate of $80M, a base estimate of $175M, and a high estimate of $380M. The merged entity's scale advantage, 290 million learners and $2.5 billion in enterprise relationships (Coursera, 2026), creates structural barriers that organic growth alone cannot overcome quickly. The simulation returned a mean expected loss of $187M, a 90th percentile outcome of $265M, and a probability of occurrence of 91%. This is the largest quantified risk in the assessment.

R28: Limited educational AI training data

A 3-point estimate was applied with a low estimate of $30M, a base estimate of $90M, and a high estimate of $210M. Building competitive educational AI datasets from scratch requires three to five years and $50M to $150M according to Stanford HAI (2024). The simulation returned a mean expected loss of $95M, a 90th percentile outcome of $142.5M, and a probability of occurrence of 83%.

| ID | Risk | P(Occur.) | Mean E[Loss] | P90 Loss | Priority |
| --- | --- | --- | --- | --- | --- |
| R6 | Capital Investment Overrun | 87% | $112.5M | $168M | #2 |
| R16 | Competitive Displacement | 91% | $187M | $265M | #1 |
| R28 | AI Training Data Gap | 83% | $95M | $142.5M | #3 |

Table 3. Monte Carlo simulation results (10,000 iterations)

Across all three risks, the combined base-case expected loss is $394.5M, rising to over $575M at the 90th percentile. These are not theoretical numbers. They reflect what the industry data consistently shows happens when platforms attempt to enter EdTech without the foundational infrastructure already in place.

These numbers reflect both what is happening inside the business and what is happening around it. On the business side, the Coursera-Udemy merger, Netflix's history of underestimating technology costs, and the pace of EdTech market growth all directly shaped the estimates for each risk. On the regulatory and technology side, the EU AI Act and tightening data privacy laws across jurisdictions add compliance costs that are not yet fully reflected in Netflix's planning. All of these factors were considered when building the scenario ranges and setting the probability estimates.

Risk response strategy

All three risks scored Critical, and that classification matters for response planning because it means acceptance is off the table. The strategies below reflect what is realistic to implement within the 2026–2028 window, not just what would be ideal in theory.

R6: Capital investment: Mitigate through staged gates

Avoidance is not an option since capital investment is required to enter EdTech at all, and transfer through insurance only covers a small fraction of a technology build of this scale. The most practical approach is phased capital deployment tied to specific milestones: LMS prototype completion, first 10,000 enrolled learners, and first enterprise partnership signed. Each gate requires board approval before the next tranche is released. If monthly capex variance goes above 15% of the approved budget, or scope change requests exceed three in a quarter, an independent cost review is triggered before any more money goes out. Risk owner: Chief Financial Officer and EdTech Program Director.

R16: Competitive displacement: Mitigate and share

At 91% probability and $187M in expected losses, this one cannot be accepted or ignored. Competing on price would be the wrong move entirely. It signals financial weakness and gives the merged competitor more reason to accelerate its enterprise relationships. The better approach is to focus on what Coursera-Udemy cannot easily replicate: AI-personalized learning paths built on Netflix's existing recommendation infrastructure, and exclusive content deals with instructors who bring real credibility in their fields. On top of that, Netflix needs to move fast on university and professional certification partnerships to build credentialing infrastructure it currently does not have. Those partnerships take time, which is exactly why this response needs to start before the platform launches. Risk owner: Chief Strategy Officer, accountable to the CEO.

R28: AI Training data gap: Mitigate and transfer

Waiting three to five years to build a proprietary educational dataset from scratch is simply not compatible with a 2026–2028 launch. The plan here is to combine synthetic data augmentation with licensed datasets from existing EdTech providers to close the gap faster. The transfer piece involves bringing in specialized AI vendors with educational model experience under performance-based contracts, so Netflix is not carrying all of the technical development risk internally. If a vendor cannot hit the accuracy benchmarks defined in the SLA, they bear the financial consequences. Risk owner: Chief Technology Officer and EdTech Program Director.

Key risk indicators and trigger points

The KRIs below were built around what is measurable and actionable for each risk, following the COSO principle that monitoring needs to be tied to the organization's risk appetite (COSO, 2017). For each indicator, our team started by defining what the business needs to know, then identified where that data lives internally, and finally defined how it feeds into the escalation process.

| Risk | KRI | Data Source | Green | Amber | Red | Response on Red |
| --- | --- | --- | --- | --- | --- | --- |
| R6 | Monthly capex vs budget variance (%) | Finance reporting | <5% | 5–15% | >15% | Board budget freeze + independent cost review |
| R6 | Scope change requests per quarter (#) | Program management log | 0–1 | 2–3 | >3 | Scope freeze + executive review before next tranche |
| R16 | Education subscriber MoM growth (%) | Product analytics | >8% | 4–8% | <4% by M18 | Emergency partnership acceleration + exclusive content investment |
| R16 | Credential partnerships signed (#) | Partnership tracker | >5 by M12 | 3–5 by M12 | <3 by M12 | Escalate to CEO; activate external partnership firm |
| R28 | Educational dataset completeness (%) | AI/ML engineering | >80% | 60–80% | <60% | Activate synthetic data augmentation + license procurement |
| R28 | AI recommendation accuracy vs benchmark | A/B testing platform | >70% | 55–70% | <55% | Escalate to CTO; activate third-party AI vendor contract |

Table 4. KRI threshold and escalation framework

Conclusion

Netflix's proposed EdTech expansion is a high-risk move, but the analysis in this report suggests it is not an unmanageable one. The three critical risks identified, capital investment overrun, competitive displacement by the merged Coursera-Udemy entity, and the educational AI training data gap, are serious individually and more serious together because they share the same root problem. Netflix is trying to enter a market that takes years to build the right relationships and infrastructure in, and it is starting that process at a moment when its main competitor just got significantly larger and better resourced.

The numbers make the stakes clear. Combined base-case expected losses reach $394.5M, with R16 alone carrying a 91% probability of occurrence and $187M in expected losses. At the 90th percentile, total exposure exceeds $575M. These are not theoretical projections. They are grounded in real EdTech market data and Netflix's own financial history. The path forward is not to walk away from the expansion but to approach it differently: phased capital deployment with hard gates, a competitive strategy built around differentiation rather than price, and a credentialing partnership program that starts well before the platform launches. The I&W thresholds and KRI framework in this report exist precisely to give the team early warning when any of those three things is not working.

One additional KRI worth monitoring beyond the three primary risks is course completion rate among enrolled learners. The EdTech industry average for open online courses sits around 15% (Class Central, 2024), and anything below 10% in Netflix's first year would signal that the product experience is not meeting learner expectations. A rate below 10% by month 12 should trigger a content design and UX review before the problem becomes visible externally.

Future Risks for Netflix

Two risks outside the 2026-2028 window are worth flagging now. The EU AI Act, which entered full enforcement in 2026, classifies AI systems used in education as high-risk, meaning Netflix's personalization engine would require ongoing transparency audits and bias testing that are not currently factored into the build cost estimates. The other risk is the rise of AI-native EdTech competitors, companies built from scratch on large language models rather than human-produced content. Both Netflix and the incumbents were built on the assumption that content creation is expensive and slow. An AI-native entrant changes that assumption entirely.

Future Risks for the EdTech Industry

Two industry-level shifts are worth monitoring. The first is credential inflation. As micro-credentials and digital certifications multiply across platforms, employers are starting to question how much weight they should carry. If that skepticism grows, the business model that most EdTech platforms depend on becomes a lot less stable, and Netflix would not be immune. The second is regulatory fragmentation. Student data privacy laws are tightening and diverging across jurisdictions at the same time. For a platform operating in 190 countries, that creates a compliance burden that gets harder to manage the more the platform grows, and the penalties for getting it wrong have already been demonstrated by FERPA and GDPR enforcement actions elsewhere.

References

Class Central. (2024). MOOC completion rates: The data. Class Central. https://www.classcentral.com/report/mooc-completion-rates-the-data/

COSO. (2017). Enterprise risk management: Aligning risk with strategy and performance. Committee of Sponsoring Organizations of the Treadway Commission.

Coursera. (2026). Coursera completes combination with Udemy. Business Wire. https://investor.coursera.com/news/news-details/2026/Coursera-Completes-Combination-with-Udemy

Gartner. (2024). EdTech platform benchmarks and cost analysis. Gartner Research.

HolonIQ. (2024). Global EdTech market intelligence report. HolonIQ.

Khadem, M., et al. (2018). Quantitative risk management in gas injection project. International Journal of Engineering, 31(2).

Mordor Intelligence. (2026). Digital education market size & share analysis. Mordor Intelligence. https://www.mordorintelligence.com/industry-reports/digital-education-market

Netflix, Inc. (2025). 2024 annual report. Netflix Investor Relations. https://ir.netflix.net/financials/annual-reports-and-proxies/default.aspx

Pantano, R. (n.d.). Introduction to risk management [Course presentation, Modules 1–5]. ALY6130, Northeastern University.

Stanford HAI. (2024). AI index report 2024. Stanford University Human-Centered Artificial Intelligence. https://aiindex.stanford.edu/report

Annex 1: Risk Treatment and Response Plan

R6 — Initial Capital Investment Exceeding Projections

| Risk Owner | Chief Financial Officer / EdTech Program Director |
| --- | --- |
| Category | Financial |
| Qualitative Score | 81 - Critical (Probability: 9, Severity: 9) |
| Quantitative P(Occur.) | 87% |
| Expected Loss | $112.5M mean / $168M at P90 |
| Distribution | 3-Point Estimate: Low $50M, Base $125M, High $250M |
| Contributing Factors | 1) No EdTech LMS exists; build cost $100–150M (Gartner, 2024) 2) Netflix gaming entry demonstrated pattern of cost underestimation 3) Scope creep risk from stakeholder feature requests during build |
| Controls | 1) Staged investment gates tied to measurable milestones 2) Independent cost review if variance >15% 3) Scope freeze requiring board approval for changes |
| Treatment Strategy | Mitigate - phased capital deployment with board-level gates |
| KRI Red Trigger | Monthly capex variance >15% OR >3 scope changes per quarter |
| Response on Trigger | Board budget freeze + independent cost review before next tranche |
| Residual Risk | Medium - controls reduce likelihood of overrun but do not eliminate it |

R16 — Coursera-Udemy Competitive Displacement

| Risk Owner | Chief Strategy Officer / CEO |
| --- | --- |
| Category | Competitive |
| Qualitative Score | 81 - Critical (Probability: 9, Severity: 9) |
| Quantitative P(Occur.) | 91% - Highest of the three risks |
| Expected Loss | $187M mean / $265M at P90 - Largest quantified risk |
| Distribution | 3-Point Estimate: Low $80M, Base $175M, High $380M |
| Contributing Factors | 1) Merger created 290M-learner platform with $2.5B valuation and 18,000 enterprise clients 2) Netflix has no credential partnerships or accreditation relationships 3) Enterprise EdTech sales cycles are 6–18 months; Netflix starts from zero |
| Controls | 1) AI-personalized learning paths leveraging existing recommendation infrastructure 2) Fast-track university and professional certification partnerships 3) Exclusive instructor content deals |
| Treatment Strategy | Mitigate (differentiation) + Share (credential partnerships) |
| KRI Red Trigger | MoM subscriber growth <4% by month 18 OR fewer than 3 partnerships by month 12 |
| Response on Trigger | Emergency partnership acceleration + exclusive content investment activated |
| Residual Risk | High - structural competitive advantage of merged entity cannot be fully mitigated within 18 months |

R28 — Limited Educational AI Training Data

| Risk Owner | Chief Technology Officer / EdTech Program Director |
| --- | --- |
| Category | Technical |
| Qualitative Score | 81 — Critical (Probability: 9, Severity: 9) |
| Quantitative P(Occur.) | 83% |
| Expected Loss | $95M mean / $142.5M at P90 |
| Distribution | 3-Point Estimate: Low $30M, Base $90M, High $210M |
| Contributing Factors | 1) Netflix recommendation data is entertainment-specific; educational AI requires different training sets 2) Building educational datasets from scratch takes 3–5 years and $50–150M (Stanford HAI, 2024) 3) Risk of biased recommendations if undertrained models are deployed prematurely |
| Controls | 1) Synthetic data augmentation program 2) License existing educational datasets from EdTech providers 3) Third-party AI vendor contracts with performance-based SLAs |
| Treatment Strategy | Mitigate (data acceleration) + Transfer (vendor SLAs) |
| KRI Red Trigger | Dataset completeness <60% OR AI recommendation accuracy <55% in A/B testing |
| Response on Trigger | Activate synthetic data program + third-party AI vendor contract |
| Residual Risk | Medium - vendor transfer and data licensing reduce technical exposure significantly |