In_Class Activity- Risk Response Planning

Using the risk he at map, quantitative and qualitative risk assessment from your prior activity as a guid, develop the risk responses

Considerations:

Brainstorm and develop risk response plans for the top-priority critical risks.

Consider applicable response strategy (risk avoidance, mitigation/reduction, transfer, acceptance) and justify your choice for the risk(s) under consideration.

Note: critical thinking and creativity is required for this activity

Based on the heatmap created for the risk assessment, we selected the following 3 risks for analysis because they all have the highest risk scores, 81 points.

R6 — Capital Investment Exceeding Projections

Response strategy: Mitigation

We chose mitigation for this one because avoiding it completely doesn't make sense because you can't enter EdTech without spending money, and transferring the risk through insurance won't cover the bulk of a technology build. So, the most practical approach is to break the investment into phases, where each release of funds depends on hitting a specific milestone, like completing the LMS prototype or reaching the first 10,000 enrolled users. If spending goes more than 15% over budget or the team requests more than 3 scope changes in a quarter, that triggers a formal review before more money goes out. The risk owner would be the CFO working alongside the EdTech program director.

R16 — Coursera-Udemy Competitive Displacement

Response strategy: Mitigation and sharing

This one is the hardest risk to deal with because at $187M expected loss you can't just accept it and move on, and you can't avoid it without scrapping the whole EdTech idea. We decided for a combination of mitigation and sharing strategy. On the mitigation side, Netflix needs to stop trying to compete head-to-head on price and instead focus on what the merged platform can't easily replicate, which is AI-personalized learning built on top of Netflix's existing recommendation engine and exclusive content deals. On the sharing side, partnering with universities and corporations to offer recognized credentials gets Netflix credibility much faster than building it alone. If subscriber growth falls below 4% month-over-month by month 18, that's the signal to accelerate partnerships urgently.

R28 — Limited Educational AI Training Data

Response strategy: Mitigation and transfer

For this risk we choose a mix of mitigation and transfer. Waiting 3 to 5 years to build a proprietary dataset from scratch is not realistic given the competitive window. So, the plan is to combine synthetic data generation with licensed datasets from existing EdTech providers to speed things up, while also contracting specialized AI vendors who already have educational model experience. That second piece transfers part of the build risk to a third party under performance-based contracts, so Netflix isn't carrying all of it internally. The trigger here is if dataset completeness drops below 60% or if the recommendation accuracy in testing falls below 55%.